## Лист1
Выбрать роли для каждого кейса, которым будет отправлено письмо. | ● Customer | ● Sales manager | ● Office manager | ● Project manager | ● Team lead | ● QA Engineer
| ● CEO | ● Business development manager | ● HR manager | ● Product manager | ● Tech lead | ● Designer
| ● CTO | ● Account manager | ● Recruitment manager | ● Product owner | ● Back-end developer | ● UI/UX specialist
| ● CFO | ● Support manager | ● Financial manager | ● Project coordinator | ● Front-end developer | ● System architect
| ● COO | ● Marketing manager |  | ● Scrum master | ● iOS developer | ● DevOps
| ● CMO |  |  | ● Business analytic | ● Android developer | ● System administrator
кейс 1 | 1. Вы получили запрос от части команды на необходимость внедрения новой непроверенной технологии на 4 неделе разработки проекта. У проекта очень сложная архитектура... Решить кейс: выбрать необходимых получателей, понять плюсы/минусы внедрения технологии в вашем проекте, принять решение о внедрении.
|  | роль (1 или несколько ролей) |  | роль (1 или несколько ролей) |  | роль (можно без ролей)
решение кейса 1 | кому: | Product Manager, Product Owner, Customer | копия: | CTO, Tech Lead, HR | скрытая копия (BCC): | Team Lead, System Architect, QA Engineer
| тема письма: | [Important, Non-urgent] Project change: new technology integration
| тело письма: | Dear all! Hope you are doing great. Currently, we are on the fourth week of the product development, and I would like to say that with this pace we can definitely meet our deadlines. Nevertheless, recently I got the request from our dev team for new technology implementation into the project development process. Taking into account very complex architecture of the project, it is highly important to get your approval in order to proceed. Thus, after analyzing pros and cons of implementation with the team I would like to state the following: 1) The implementation of the technology will add extra important features to the product that are new for this market. Thus, it can be additional market advantage; 2) This technology can provide extra functionality for end users, which can improve user experience; 3) As the technology is not fully tested and completely new, we might require extra QA specialists in order to cover it with all necessary test cases. Besides, we require 2 more developers in order to implement this technology in time, without postponing the release date; 4) The major risk of the implementation is the risk of mismatching with the product architecture and roll-back to the prior state. Nonetheless, in case of success, this will add extra market value to company in perspective. After evaluation of the risks and double-checking the risk tolerance, we can assure that implementation of the technology is possible without changing the deadlines. Attaching you all required assessment documentation to check this on your side. Please, provide us with your approve, so we could initiate the implementation process. Looking forward to hearing from you. Best,
| подпись | Olga Kholodkova, Connect.Pet Project Manager, connect.petdaopmt2@gmail.com
кейс 2 | 2. Вы обнаружили несколько противоречий в последовательности процессов разработки (перепутаны даты старта работы некоторых разработчиков/разработка начинается раньше чем отрисовка макетов). Проект был передан вам другим ПМом некоторое время назад, и вы уверены, что данные погрешности отразятся на проекте в целом... Решить кейс: выбрать необходимых получателей, провести анализ, разрешить ситуацию.
|  | роль (1 или несколько ролей) |  | роль (1 или несколько ролей) |  | роль (можно без ролей)
решение кейса 2 | кому: | Customer | копия: | Scrum master, Product manager, Financial manager | скрытая копия (BCC): | Team Lead, Designer, UX/UI
| тема письма: | [Important, Urgent] Project processes change
| тело письма: | Hello there! Hope you are doing great. Reaching you out to disscuss with you the project processes. After examining the process chart that has been passed to me from previous Project Manager, I noticed some errors in project planning. Briefly speaking, the development process of the product starts prior the final delivery of the product mock-ups. The overlaping of this two processes will influence the project overally in terms of timing. As the original timeline has been approved, I am requesting the overlook of the processes in order to adjust the timing properly and minimizing the risk of not meeting the deadlines. As thi is highly important and urgent, I would like to provide you with the best possible solution. The main suggestion here would be decomposing the mock-ups development process into four sub-processes with four approval meetings. Such decomposition will extend this process for 6 days due to extra approval and possible mock-up changes. Nevertheless, prior the start of the development process by our dev team, we would be able to deliver 50% of the mock-ups, which provide us with the necessary basis to work without interuptions or postponing the deadlines of the project. Per my estimations, the prolongation of the designer and UX/UI work will add 15% to the total costs incorporated to the process. Per contra, in this case we end the developers work two days earlier, which reduce the cost of this process, so the total project cost will not be affected. Please let me know when would it be possible to have a call in order to discuss this matter. Looking forward to your response. Best,
| подпись | Olga Kholodkova, Connect.Pet Project Manager, connect.petdaopmt2@gmail.com
кейс 3 | 3. Команда вам сообщила, что вам в проекте необходимо два дополнительных специалиста, чтобы успеть запустить проект к релизу. Специалисты могут могут быть как наняты извне, так и привлечены из других внутренних команд компании. Решить кейс: выбрать необходимых получателей, объяснить кто нужен и доказать потребность в этих специалистах, утвердить их.
|  | роль (1 или несколько ролей) |  | роль (1 или несколько ролей) |  | роль (можно без ролей)
решение кейса 3 | кому: | CTO, COO | копия: | HR, Recruiter, Financial | скрытая копия (BCC): | Team Lead, Scrum master
| тема письма: | [Important, Urgent] Request for additional developers
| тело письма: | Hello CTO and COO! Reaching you out with the request to alocate two additional Back-End developers in order to meet the product release deadline. Both developers can be hired from the outside or temporarily moved from other projects if it is possible. Speaking about project budget, we can cover both the inhouse developers, as well as from the outside. Without this step, we have critical risk of not delivering the product in time, postponing it for a week. This will result in financial penalty for us. Please let us know as soon as possible. Best,
| подпись | Olga Kholodkova, Connect.Pet Project Manager, connect.petdaopmt2@gmail.com
кейс 4 | 4. По итогу нескольких спринтов вы осознали, что в релизных версиях (которые вы демонстрируете заказчику) остается слишком много пропущенных ошибок. Некоторые из этих ошибок повторяются не первый раз. Клиент злится. Решить кейс: выбрать необходимых получателей, выяснить почему так вышло, объяснить и разрешить ситуацию.
|  | роль (1 или несколько ролей) |  | роль (1 или несколько ролей) |  | роль (можно без ролей)
решение кейса 4 | кому: | Team Lead, Tech Lead, Scrum Master | копия: | CTO, BA | скрытая копия (BCC):
| тема письма: | [Critical, Urgent] Errors bulking!
| тело письма: | Hello Team! This is an urgent email, thus do not disregard this. Recently, I got another report from our valued customer regarding continuous issues in the product releases (three releases in the row). I am requesting the logs and history of assigned task for the last three sprints, as well as QA tasks, in order to analyze and check if these tasks were handled appropriately.
| подпись | Olga Kholodkova, Connect.Pet Project Manager, connect.petdaopmt2@gmail.com
кейс 5 | 5. На сейчас у вас завершился текущий и, на данный момент, финальный этап разработки. Вам необходимо выяснить какой дальнейший план действий по проекту... Решить кейс: выбрать необходимых получателей, выяснить дальейшие планы и цели, спланировать.
|  | роль (1 или несколько ролей) |  | роль (1 или несколько ролей) |  | роль (можно без ролей)
решение кейса 5 | кому: | Customer | копия: | BizDev, CEO | скрытая копия (BCC): | Support
| тема письма: | [Regular, Non-urgent] After project follow-up
| тело письма: | Hello Customer! Hope you are doing great. As you know we successfully finished the project and delivered the product to you. I believe, this was a great experience and collaboration for you. Speaking about that, we would like to discuss with you our potential steps for continuing our partnership. I am CCing here our CEO and Business Development Manager in order to negotiate possible customer support or, probably, further projects. Please let us know about your intentions, so we could provide you with the proper cooperation solutions. Best,
| подпись | Olga Kholodkova, Connect.Pet Project Manager, connect.petdaopmt2@gmail.com